## Sheet1
S.No | Feature/User Story | Feature Name | Feature Description | Priority | Acceptance Criteria | Estimated Effort (Story Points) | Order
1 | Landing Page | Home Page | UI design of the home page |  |  | 5
1.1 |  |  | Course Title (The Cloud Triad: A comparative journey through AWS, GCP and Azure essentials) and description(mention about the comparison, industrial usage, pricing/cost effectiveness, sustainability). Probably include a graph with the mentioned stats.
1.2 |  |  | What do you gain from this course - precise information
1.3 |  |  | Start Course Button
2 | Landing Page | Second Page | High Level View in a picture, which entails the data within the course (all elements) |  |  | 5
2.1 | Landing Page |  | Add visually appealing elements like images, animations, to explain what the user is going to learn about |  |  | 5
2.2 | Landing Page |  | Sequence of learning will be mentioned (with the images) |  |  | 5
3 to 32 |  | Course Topics
3 |  | Compute
3.1 |  |  | Virtual Machines
3.2 |  |  | Serverless Computing
4 |  | Container Services
4.1 |  |  | Container Orchestration
4.2 |  |  | Container Management
4.3 |  |  | Container Registry
5 |  | Storage
5.1 |  |  | Object Storage
5.2 |  |  | Block Storage
5.3 |  |  | File Storage
5.4 |  |  | Archive Storage
5.5 |  |  | Backup/Restore
6 |  | Database
6.1 |  |  | Relational Database
6.2 |  |  | NoSQL Database
6.3 |  |  | Data Warehouse
7 |  | Networking
7.1 |  |  | Virtual Private Network
7.2 |  |  | Content Delivery Network
7.3 |  |  | DNS
7.4 |  |  | Firewall
7.5 |  |  | Load Balancing
8 |  | Security
8.1 |  |  | Identity & Access Management
8.2 |  |  | Key Management Service
8.3 |  |  | Security Monitoring
9 |  | Analytics
9.1 |  |  | Big Data Processing
9.2 |  |  | Stream Analytics
9.3 |  |  | Business Intelligence
10 |  | Data Management
10.1 |  |  | Data Integration
10.2 |  |  | Data Lake
11 |  | AI & Machine Learning
11.1 |  |  | Machine Learning Platform
11.2 |  |  | Natural Language Processing
11.3 |  |  | Object Detection/AI
11.4 |  |  | Speech Recognition
12 |  | DevOps
12.1 |  |  | Continuous Integration/Continuous Deployment
12.2 |  |  | Infrastructure as Code
13 |  | Monitoring & Logging
13.1 |  |  | Logging
13.2 |  |  | Monitoring
14 |  | IoT
14.1 |  |  | IoT Platform
14.2 |  |  | Edge Computing
15 |  | Migration & Transfer
15.1 |  |  | Data Transfer Service
16 |  | Management & Governance
16.1 |  |  | Resource Management
16.2 |  |  | Cost Management
17 |  | Hybrid & Multi-cloud
17.1 |  |  | Hybrid Cloud Service
18 |  | Quantum Computing
18.1 |  |  | Quantum Computing Service
19 |  | Blockchain
19.1 |  |  | Blockchain Service
19.2 |  |  | Blockchain Templates
20 |  | Robotics
20.1 |  |  | Robotics Service
20.2 |  |  | Robotics Development
21 |  | Satellite
21.1 |  |  | Satellite Service
21.2 |  |  | Ground Station Service
22 |  | Game Development
22.1 |  |  | Game Development Service
22.2 |  |  | Game Server Hosting
23 |  | Augmented Reality (AR) & Virtual Reality (VR)
23.1 |  |  | AR/VR Development
24 |  | Business Applications
24.1 |  |  | Customer Relationship Management (CRM)
24.2 |  |  | Enterprise Resource Planning (ERP)
24.3 |  |  | Office Productivity Suite
24.4 |  |  | Project Management
24.5 |  |  | Business Intelligence
25 |  | Developer Tools
25.1 |  |  | API Management
25.2 |  |  | Integrated Development Environment (IDE)
25.3 |  |  | Artifact Repository
25.4 |  |  | Code Repository
25.5 |  |  | Dev Environment
26 |  | Application Integration
26.1 |  |  | Workflow Orchestration
26.2 |  |  | Messaging Service
27 |  | Desktop as a Service (DaaS)
27.1 |  |  | Virtual Desktops
27.2 |  |  | Managed Desktops
28 |  | Email Services
28.1 |  |  | Email Sending Service
28.2 |  |  | Managed Email
29 |  | Search Services
29.1 |  |  | Search Engine Service
29.2 |  |  | Enterprise Search
30 |  | Media Services
30.1 |  |  | Video Processing
30.2 |  |  | Live Streaming
31 |  | Mobile Services
31.1 |  |  | Mobile App Development
32 |  | Contact Center
32.1 |  |  | Cloud Contact Center
Note on G1: S, Reetika: 1, 3, 5, 7, 9, 11, 13, 15